## Sprint0
ISCG 7427 Agile and Lean Software Delivery |  |  | Assignment Semester 1, 2019
Team: Minions
Vision: For Customers , Who like to do shop anything and anytime from anywhere but does not have the enough time to try all products at a store or by trying them on online The "Augmented Reality AR Application " Is mobile application that allows shoppers to virtually try clothes, shoes and everything and its is just far away to one click the app as a customer scan the mobile towards the product automatically appesrs on them or by clicking on product online they can select and make choice whatever they want . Unlike Other Shopping /Online Shopping App This application saves a lot of time not only by avoid trial rooms but also can try through online shopping and allows for a much instead service. |  |  | Team Roles:
|  |  | 1 | Scrum Master: Sahil Shah, 1505247
|  |  | 2 | Product Owner: Bhuvan Khanna, 1512544
|  |  | 3 | Team Members: 1)Meichen Zhou, 1505251 2)Reena Kumari Lohana, 1498290 3)Resmi Kizhakkekuttu Jose, 1492400
Priority | User Story | Acceptance Criteria | Sprint # | Story Points | Task List | Sprint Planning |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Sprint Review & Restrospective |  |  |  | Comments on Sprint Review and Sprint Retrospective
[6 empty] | 13/03/2019 |  |  |  | 20/03/2019 |  |  |  | 27/03/2019 |  |  |  | 2019-04-03 |  |  |  | 2019-04-10 |  |  |  | 2019-05-08
[6 empty] | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete
1 | As a shopper, I want to register, so that I can login the application | 1) The Maximum length of user name should be 20 characters 2) The password must contains atleast 6 and the maximum length 100 characters long 3)Password must be at least 8 characters and must have atleast one uppercase (A-Z) 4) The user can only be able to register if he/she enter an security code that is being received on mobile number 5) If the username is already in database, message should be pop up showing that user already exists 6) The user should be able to register using their email id or mobile number | 0 | 5 | a)Design the register page b)Design database c)Insert validations for all fields in register page d) write the necessary code for register and database. E) Create and Test Cases for this feature. | [24 empty] | Inserting validation for the registration field was quite challenging but our developers ensure that all validations were inserted. All validations were tested to ensure that all the requirements have been meet
2 | As a shopper, I want to login the application, so that I can view all the products onlinp | 1) If the username and password matched to the details in database, display the message showing login successfully, and redirect to the home screen 2) If the username and password doesn't match, dislay error message showing invalid details and please try again 3) If the user click "forget password", redirect to the forget password page, and then the user can reset the password 4) Only the registered users login to the application, and they can see the products | 0 | 3 | a)Design the login page b)Insert validations for all fields in login page c)Verify the credentials of username and password with database d)Create necessary alert for the failed login | [24 empty] | Writing the logic to recover the password was a big task. However, the team achieved the task. The logic was testing multiple times to ensure that password recovery option worked successfully.
3 | As a shopper, I want to see all the products, so that I can select the product | 1) The User who already login can see the products 2) User can select the products by click on Product Button 3) The Product image , Price and product name will displays in the product list. | 0 | 2 | 1) Create the product list page. 2) Create the link to the product details page 3)Create ethe product button on home page 4) fetch data from Product Data Table . | [24 empty] | This task was easy and was achieved successfully.
4 | As a shopper, I want to select one product, so that I can add that product in the shopping cart | 1) The user can select the multiple products at once 2) The user can click "add to cart" button, and the selected products will be displayed in the shopping cart | 0 | 5 | 1) Create code for "select" button and "add to cart" button 2) Design and create shopping cart page 3) Design and create the database for shopping cart | [24 empty] | This task was not thay much easy as team memebrs create database to save the products and all details.
5 | As a shopper, I want to delete the selected product, so that I can remove the unwanted items | 1) The user can discard the product from shopping cart by clicking the "remove" button 2) If the shopping cart is empty after removing the product, then redirect to the home screen | 0 | 3 | 1) Create functionality for "select" button and "remove" button 2) Write code for navigation to home screen when the shopping cart is empty | [24 empty] | This task was achieved easily. This task was tested multiple times to ensure its added in cart or not.
6 | As a shopper, I want to enter my card details, so that I can get my product for every payment | 1) The card like VISA, Mastercard, American Express are supoorted 2) If the card details are valid, then redirect to the payment gateway process 3) If the card details are invalid, then error message displays | 0 | 3 | 1) Include 3-party APIs to access to the bank systems 2) Create code for displaying invalid message on the screen 3) Create payment page | [24 empty] | This Task was not much difficult but our developers are familiar with this part.
7 | As a Shopper , I want to logout from the AR App account. | 1) The User can click Logout Button only when he is already Login. 2) The User Navigate to Login page after clicking Logout button 3) Display Confirm message to make sure the user want to logout from account. | 0 | 3 | 1) Create Logout Button 2) Create Confirm Dialoug Box 3) Write code to control the authentication | [24 empty] | This task was easy and was achieved successfully.

## Sprint1
ISCG 7427 Agile and Lean Software Delivery |  |  | Assignment Semester 1, 2019
Team: Minions
Vision: For Customers , Who like to do shop anything and anytime from anywhere but does not have the enough time to try all products at a store or by trying them on online The "Augmented Reality AR Application " Is moblie application that allows shoppers to virtually try clothes, shoes and everyhing and its is just far away to one click the app as a customer scan the mobile towards the product automatically appesrs on them or by clicking on product online they can select and make choice whatever they want . Unlike Other Shopping /Online Shopping App This application saves a lot of time not only by avoid trial rooms but also can try through online shopping and allows for a much instead service. |  |  | Team Roles:
|  |  | 1 | Scrum Master: Sahil Shah, 1505247
|  |  | 2 | Product Owner: Bhuvan Khanna, 1512544
|  |  | 3 | Team Members: 1)Meichen Zhou, 1505251 2)Reena Kumari Lohana, 1498290 3)Resmi Kizhakkekuttu Jose, 1492400
Priority | User Story | Acceptance Criteria | Sprint # | Story Points | Task List | Sprint Planning |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Daily Stand up meeting |  |  |  | Sprint Review & Retrospective |  |  |  | Comments on Sprint Review and Sprint Retrospective
[6 empty] | 2019-04-15 |  |  |  | 2019-04-17 |  |  |  | 19/04/2019 |  |  |  | 2019-05-01 |  |  |  | 2019-05-20 |  |  |  | 2019-05-27 |  |  |  | 2019-06-03 |  |  |  | 2019-06-10 |  |  |  | 2019-06-12
[6 empty] | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete | Yet to Start | Dev in Progress | Under Test | Complete
8 | As shopper, I want to select gender option, so that I can try the categories according to my gender. | 1)The user can click on gender option 2)The user should select options from different categories including clothes,accessories and shoes. | 1 | 5 | 1)Create the radio button to select the gender option 2)Design the page 3)Create options for different categories 4)Create database for different categories | [36 empty] | -task was easy and developers completed successfully without any trouble.
9 | As Shopper, I want to enter my body details, so that my body size can be recorded by the system. | 1)The user can click on "detail" button 2)The user should input the height,chest,waist measurements . | 1 | 8 | 1)Design the body details page 2) Create predefined body types 3) Create customized body types where the user can add new measurements 4)Create "detail" button 5)Create database for body measurements 6)Create input textboxes 7)Create "save" button | [36 empty] | -task was easy and completed successfully without any trouble.
10 | As a shopper, I want to edit my body size details, so that I can update my details of the selected product | 1) Click on the "edit" tab, redirecting to "body type" page 2) Predefined body types are provided on the page, the user can select the predefined measurement according to their own type 3) Customized body types are provided | 1 | 8 | 1) Update database with new details 2) Design body edit page | [36 empty] | This was long task and took more days more than estimated days as the developers also faced coding -issues in edit section
11 | As a shopper, I want to select the skin tone from the options,so that I can choose my skin tone. | 1)The user can select "skin tone "button. 2)Choose desired skin tone. 3)The user can click on "OK" button. | 1 | 8 | 1)Create the options of different skin tones 2)Create popup windows for showing skin tones 3)Create "OK" button | [36 empty] | -This task was easy and everything goes well in this user story
12 | As a shopper, I want to see how the clothes suits on my body , so that I can add to the cart. | 1)The user can click on "AR view" button. 2)The camera should be open. 3)The camera should recognize the body 4) The user can click the "Add to cart" button after selecting the item | 1 | 10 | 1)Design the page 2)Create "AR view" button 3)Write functionality to recognize the body 4)Create "Add to cart" button | [36 empty] | -This was toughest part compared to all other user stories so far executed. -Implementing the functionality was a tough task ,but executed with more attention.
13 | As a shopper, I want to swipe the color options, so that I can try different colors of the same clothes. | 1)The user can click on "AR view" button. 2)The camera should be open. 3)The camera should recognize the body 4)The user can swipe to select the different colors. | 1 | 10 | 1)Create options for different colors 2)Create swipe functionality | [36 empty] | -Got defects during testing ,but able to correct those defects. -Successfully completed this user-story.
14 | As a shopper, I want to be able to take a screenshot ,so that I can save and share the picture. | 1)The user can click on "AR view" button. 2)The camera should be open. 3)The camera should recognize the body 4)The user can click on "screenshot" button, then confirmation message will display showing "save", "delete" or "share". | 1 | 10 | 1) Create "screenshot" button 2)Write the necessary code to show the confirmation 3)Create "save", "delete", "share" button 4)Create functionality for save, delete, share | [36 empty] | -Task was easy to set up ,although it took time. completed successfully without any trouble.
15 | As a shopper, I want to be able to change the background ,so that I can get the perfect look according to occasion. | 1)The user can click on "AR view" button. 2)The camera should be open. 3)The camera should recognize the body 4)The user can select the option to change the background 5)The user can click on "screenshot" button, then confirmation message will display showing "save", "delete" or "share". | 1 | 10 | 1)Create predefined backgrounds 2)Create "choose background" button 3)Write code to change background after clicking button | [36 empty] | -task was easy and developers completed successfully without any trouble.